## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-02-d
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  |  | PASS | QH; 4/1/2018
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  |  | PASS | QH; 4/1/2018
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  |  | PASS | QH; 4/1/2018
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  |  | PASS | QH; 4/1/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  |  | PASS | QH; 4/1/2018
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  |  | PASS | QH; 4/1/2018
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. |  |  | PASS | QH; 4/1/2018
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  |  | PASS | QH; 4/1/2018
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  |  | PASS | QH; 4/1/2018
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  |  | PASS | JE; 4/2/2018
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  |  | PASS | JE; 4/2/2018
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  |  | PASS | JE; 4/2/2018
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  |  | PASS | JE; 4/2/2018
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  | PASS | JE; 4/2/2018
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  | PASS | JE; 4/2/2018
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  | PASS | JE; 4/2/2018
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  |  | PASS | JE; 4/2/2018
As a User I want to display american rules so that I know how to play American Checkers. | Given that I am at the home screen when I click on the "Rules" link then I expect to be directed to a page with the American checkers rules. |  |  | PASS | SL; 3/31/2018
| Given that I am in a game when I click on a "Rules" link then I expect to be prompted with the American checkers rules overlapped with my current game. |  |  | Pass | SL;3/31/2018
As a player, I want to resign my game at any point so that I can forfeit. | Given I'm in a game with my opponent when my opponent forfeit by either clicking the "Forfeit" button or closing the browser then I expect to be notified on my page and win this game. |  |  | Pass | BD;4/2/2018
| Given that I am in a game when I click the "Forfeit" button then I expect to end my turn, leave the game, and be directed to the home page. |  |  | PASS | BD;4/2/2018
As a player I want to be able to drag and drop valid checker pieces so that I can make a move during a game. | Given it is my turn when I drag and drop a piece to a new valid position then I expect my dragged piece to move to the new position, and the jumped over opponent's piece is taken off the board (if there is any) |  |  |  |  | PASS | SL; 4/18/2018
| Given that my piece can jump another piece, when I try to avoid this then, that move should be invalid |  |  |  |  | PASS | SL; 4/18/2018
Given that I can do a multi-jump when I do the first jump I expect my turn not to end until the end of my multiple jump
As a player I would like to have enhancements to improve my checkers playing experience | Given I am finished a game, then expect to be able to replay that game from the beginning so that I can improve my strategy |  |  |  |  | PASS | BD; 4/18/2018
| Given that I am a player, then I expect to be able to ask the game for help so that I am not stuck when taking a turn |  |  |  |  | PASS | BD; 4/18/2018
As a player I would like to be able to know if I win or not at the end of a game | Given that I'm in a game when I have taken off all my opponent's pieces then I expect to be redirected to the result page showing that I win. |  |  |  |  | PASS | QH; 4/18/2018
| Given that I'm in a game when all my pieces are taken off the board by my opponent, then I expect to be redirected to the result page showing that I lose. |  |  |  |  | PASS | QH; 4/18/2018
As a Player want to be given help in-game so that I will have a better understanding of the game | Given I am currently playing a game when I ask for help during my turn then I will see my available moves |  |  |  |  | PASS | JE; 4/18/2018
| Given I currently need help when I ask for help then then it should give out a tip to help me decide a move |  |  |  |  | PASS | JE; 4/18/2018
As a player I want to have my checker pieces marked as king pieces if they ever reach the opponent’s end so that I can distinguish them during the game to make smarter moves. | Given that it is my turn, when I move my piece to the other side of my board, I expect that piece to turn into King. |  |  |  |  | PASS | JM; 4/18/2018